## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## GANTT
Prediction of hotel reservation cancellation of a customer with reservation details using Machine Learning
University of Hertfordshire, Nikhil Reddy Marella, 20067093
| Milestone description | Progress | Start | End | Days
0
Project Idea | Data Source and Project Idea | 100% | 2023-02-23 | 2023-02-24 | 2
| Data Understanding | 100% | 2023-02-23 | 2023-02-24 | 2
| Hypothesis Identification | 100% | 2023-02-25 | 2023-02-25 | 1
| Detailed Project Prososal (DPP Report) | 100% | 2023-02-26 | 2023-03-02 | 5
| DPP Submission | 100% | 2023-03-07 | 2023-03-07 | 1
Literature Background | Hotel reservation cancellation papers | 100% | 2023-03-10 | 2023-03-10 | 1
| Best Classification Algorithms | 70% | 2023-03-11 | 2023-07-31 | 143
| RF, DCS, KNN, K-Means, Naïve Bayes | 80% | 2023-03-11 | 2023-07-31 | 143
| Cross Validation Techniques | 80% | 2023-03-11 | 2023-07-31 | 143
Data Cleaning | Deal with missed values in Columns | 100% | 2023-03-17 | 2023-03-17 | 1
| Drop any null value rows | 100% | 2023-03-17 | 2023-03-17 | 1
Data Preparation and Visualization | Understanding visualization Plots | 100% | 2023-03-18 | 2023-03-18 | 1
| learn code for plotting the charts | 100% | 2023-03-19 | 2023-03-19 | 1
| Plot histograms for all columns | 100% | 2023-03-20 | 2023-03-21 | 2
| Plot bar plot for categorical columns | 100% | 2023-03-20 | 2023-03-21 | 2
| learn code for one hot encoding | 100% | 2023-03-22 | 2023-03-23 | 2
| One hot encode on categorical coumns | 100% | 2023-03-23 | 2023-03-23 | 1
Model Building | Split train and test | 100% | 2023-03-24 | 2023-03-24 | 1
| Standardize the data | 100% | 2023-03-24 | 2023-03-24 | 1
| Learn DCT and Random Forest theory and code | 100% | 2023-03-25 | 2023-03-28 | 3
| GridSearch for Decision Tree Classifier | 100% | 2023-03-29 | 2023-03-29 | 1
| Decision tree classifier (Best Params) | 100% | 2023-03-29 | 2023-03-29 | 1
| GridSearch for Random Forest Classifier | 80% | 2023-03-30 | 2023-03-30 | 1
| Random Forest (Best Params) | 80% | 2023-03-30 | 2023-03-30 | 1
| Test unseen data on best model | 80% | 2023-03-31 | 2023-03-31 | 1
| Interim Progress Report | 80% | 2023-04-15 | 2023-04-25 | 11
| IPR Submission | 80% | 2023-05-01 | 2023-05-01 | 1
| Hyperparameter Tuning on ML algorithms |  | 2023-05-14 | 2023-05-21 | 8
| Performance Comparision |  | 2023-05-22 | 2023-05-22 | 1
| Test unseen data on best model |  | 2023-05-22 | 2023-05-22 | 1
FPR Report | Abstract |  | 2023-05-24 | 2023-05-24 | 1
| Introduction |  | 2023-05-25 | 2023-05-27 | 3
| Literature Review Search |  | 2023-05-28 | 2023-06-10 | 14
| Data Analysis and Preparation |  | 2023-06-12 | 2023-06-20 | 9
| Model Building |  | 2023-06-21 | 2023-06-30 | 10
| Results |  | 2023-07-01 | 2023-07-03 | 3
| Conclusion |  | 2023-07-04 | 2023-07-04 | 1
| Future Work |  | 2023-07-05 | 2023-07-05 | 1
| References |  | 2023-07-05 | 2023-07-05 | 1
| Appendices |  | 2023-07-06 | 2023-07-06 | 1
| Plagarism Check |  | 2023-07-07 | 2023-07-07 | 1
| Final Edits and Review |  | 2023-07-08 | 2023-07-15 | 8
| Final Plagarism Check |  | 2023-07-16 | 2023-07-16 | 1
| Meet with Supervisor |  | 2023-07-17 | 2023-07-17 | 1
| FPR Submission |  | 2023-08-28 | 2023-08-28 | 1

## Green
Project Planning: Human Emotion Detection from the audio using Deep Learning
University of Hertfordshire, 20026202
SAIRAM KANDUKURI
Project start date: | 2023-01-25 | [11 empty] | Scrolling increment: | [5 empty] | 0 | Days Period: | [5 empty] | 4
Milestone marker: | 1 | 1 |  |  |  | January | [6 empty] | February | [6 empty] | March | [6 empty] | April | [6 empty] | May | [6 empty] | June | [6 empty] | July | [6 empty] | August
 | time axis 2023-01-25 to 2023-09-02
Milestone description | Assigned to | Progress | Start | End | Days | time axis 2023-01-25 to 2023-09-02
0
Project Idea and Data
Identifying Project Idea |  | 100% | 2023-01-25 | 2023-01-25 | 1 | bar: 2023-01-25
Identifying Data Source and connections |  | 100% | 2023-01-27 | 2023-01-29 | 2
Understanding Data |  | 100% | 2023-02-01 | 2023-02-04 | 3
Identify Hypothesis |  | 100% | 2023-02-06 | 2023-02-06 | 1
Detailed Project Prososal |  | 100% | 2023-02-06 | 2023-02-06 | 1 | bar: 2023-02-06
DPP Submission |  | 100% | 2023-02-07 | 2023-02-07 | 1
Literature Research (Identify Papers on)
Crema-D Dataset and Title |  | 90% | 2023-02-08 | 2023-05-31 | 112
Deep learning papers on emotion detection |  | 85% | 2023-02-09 | 2023-05-31 | 111
Data Augmentation for audio |  | 80% | 2023-02-10 | 2023-05-31 | 110
Features Extraction from audio |  | 100% | 2023-02-12 | 2023-05-31 | 108
Data Cleaning and Merging
Data Loading and Seperation of clipname into columns |  | 100% | 2023-02-15 | 2023-02-15 | 1
Merge VideoDemographics.csv on ActorID and get insights. |  | 100% | 2023-02-16 | 2023-02-17 | 1
Merge finishedResponses.csv with preciously merged data on ActorID |  | 100% | 2023-02-18 | 2023-02-19 | 1 | bar: 2023-02-18
Deal with missed values in Tone Column |  | 100% | 2023-02-21 | 2023-02-22 | 1
Drop any null value rows |  | 100% | 2023-02-23 | 2023-02-23 | 1
Subset the required columns from cleaned data for further analysis |  | 100% | 2023-02-23 | 2023-02-23 | 1
Data Augmentation and Feature Extarction
Understanding Librosa Library |  | 100% | 2023-03-01 | 2023-03-03 | 2
Learn Plotting the spectral waveforms |  | 100% | 2023-03-04 | 2023-03-04 | 1
Learn audio augmentation methods |  | 100% | 2023-03-07 | 2023-03-07 | 1
Implement audio augmentation methods |  | 100% | 2023-03-08 | 2023-03-08 | 1
Test noise, stretch, shift, pitch for audio files. |  | 100% | 2023-03-09 | 2023-03-09 | 1
Learn ZCR, Chroma_stft, MFCC, RMS, MEL |  | 100% | 2023-03-10 | 2023-03-12 | 2
Check code references for feature extraction. |  | 100% | 2023-03-13 | 2023-03-14 | 1
Implement feature extraction for all audio files |  | 100% | 2023-03-15 | 2023-03-17 | 2
One hot encode ToneLevel and Emotion |  | 100% | 2023-03-18 | 2023-03-18 | 1
Data Frame all extracted features |  | 100% | 2023-03-18 | 2023-03-18 | 1
Model Building
Base Line Model |  | 100% | 2023-03-22 | 2023-04-05 | 14
Analyse results |  | 100% | 2023-04-06 | 2023-04-08 | 2
Interim Progress Report |  | 100% | 2023-04-10 | 2023-04-21 | 11
IPR Submission |  | 100% | 2023-05-01 | 2023-05-01 | 0
Algorithm Experiments and hyperparameter tuning |  |  | 2023-05-13 | 2023-05-20 | 7
Performance Comparision |  |  | 2023-05-21 | 2023-05-21 | 1
Test unseen data on best model |  |  | 2023-05-22 | 2023-05-22 | 1
Dissertation Report
Abstract |  |  | 2023-05-23 | 2023-05-24 | 1
Introduction |  |  | 2023-05-25 | 2023-05-27 | 2
Literature Review |  |  | 2023-05-28 | 2023-06-10 | 13
Meet with Supervisor |  |  | 2023-06-07 | 2023-06-07 | 1
Data Analysis |  |  | 2023-06-12 | 2023-06-17 | 5
Model Building |  |  | 2023-06-20 | 2023-06-26 | 6
Results |  |  | 2023-06-27 | 2023-06-30 | 3
Conclusion |  |  | 2023-07-01 | 2023-07-01 | 1
Future Work |  |  | 2023-07-02 | 2023-07-02 | 1
References |  |  | 2023-07-03 | 2023-07-03 | 1
Appendices |  |  | 2023-07-03 | 2023-07-03 | 1
Plagarism Check |  |  | 2023-07-04 | 2023-07-04 | 1
Final Edits and Review |  |  | 2023-07-05 | 2023-07-10 | 5
Final Plagarism Check |  |  | 2023-07-11 | 2023-07-11 | 1
Meet with Supervisor |  |  | 2023-07-12 | 2023-07-12 | 1
FPR Submission |  |  | 2023-08-28 | 2023-08-28 | 1

## Blue
Project: Blue
Contoso, Ltd.
Gurpreet Bawa
Project start date: | 2023-04-27 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | May | [27 empty] | June
 | time axis 2023-05-10 to 2023-07-04
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-05-10 to 2023-07-04
Title 1
Task 1 |  | 25% | 2023-04-30 | 3
Task 2 |  |  | 2023-05-05 | 1
Task 3 |  | 50% | 2023-04-27 | 10
Task 4 |  |  | 2023-05-20 | 1 | bar: 2023-05-20
Task 5 |  | 10% | 2023-05-06 | 6
Title 2
Task 1 |  | 80% | 2023-05-06 | 14
Task 2 |  | 50% | 2023-05-07 | 9
Task 3 |  | 33% | 2023-05-15 | 11
Task 4 |  |  | 2023-05-24 | 1 | bar: 2023-05-24
Task 5 |  |  | 2023-05-25 | 24
Title 3
Task 1 |  |  | 2023-05-15 | 4
Task 2 |  |  | 2023-05-19 | 14
Task 3 |  |  | 2023-06-04 | 6
Task 4 |  |  | 2023-06-17 | 3
Task 5 |  |  | 2023-06-09 | 19
Title 4
Task 1 |  |  | 2023-06-06 | 15
Task 2 |  |  | 2023-05-29 | 5
Task 3 |  |  | 2023-07-19 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project: Purple
Contoso, Ltd.
Hayden Cook
Project start date: | 2023-04-27 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | May | [27 empty] | June
 | time axis 2023-05-10 to 2023-07-04
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-05-10 to 2023-07-04
Title 1
Task 1 |  | 25% | 2023-04-30 | 3
Task 2 |  |  | 2023-05-05 | 1
Task 3 |  | 50% | 2023-04-27 | 10
Task 4 |  |  | 2023-05-20 | 1 | bar: 2023-05-20
Task 5 |  | 10% | 2023-05-06 | 6
Title 2
Task 1 |  | 60% | 2023-05-06 | 13
Task 2 |  | 50% | 2023-05-07 | 9
Task 3 |  | 33% | 2023-05-15 | 11
Task 4 |  |  | 2023-05-24 | 1 | bar: 2023-05-24
Task 5 |  |  | 2023-05-25 | 24
Title 3
Task 1 |  |  | 2023-05-15 | 4
Task 2 |  |  | 2023-05-19 | 14
Task 3 |  |  | 2023-06-04 | 6
Task 4 |  |  | 2023-06-17 | 3
Task 5 |  |  | 2023-06-09 | 19
Title 4
Task 1 |  |  | 2023-06-06 | 15
Task 2 |  |  | 2023-05-29 | 5
Task 3 |  |  | 2023-07-19 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one